## Cover
Tejaswini Dondeti — Portfolio Sample • tejaswinidondeti.github.io • Read-only preview — please do not edit or redistribute
TechStart Inc.
Information Security Risk Register
Cloud Migration Program — ISO/IEC 27001:2022 & NIST CSF
Document ID: | TS-ISMS-RR-001
Version: | 1.0
Assessment Date: | Q3 2024
Risk Owner: | CISO / GRC Lead
Scope: | Migration of 5M+ record customer database from on-premises to AWS; associated IAM, data pipeline, and business continuity workstreams
Methodology: | ISO 31000:2018 risk management; 5x5 likelihood × impact matrix; risk treatment per ISO/IEC 27005; controls mapped to ISO 27001:2022 Annex A and NIST CSF v1.1
Scoring: | Likelihood 1–5 (Rare → Almost Certain); Impact 1–5 (Negligible → Catastrophic); Risk Score = L × I; Risk Level: 1-4 Low, 5-9 Medium, 10-14 Medium-High, 15-19 High, 20-25 Critical
Acceptance: | Risk owner signoff required for all Critical and High residual risks; Board Risk & Audit Committee notified of any residual Critical
Risk Level Legend
Critical (20-25) | Immediate action required; stop migration phase until treated
High (15-19) | Treat within current sprint; escalate to CISO
Medium-High (10-14) | Treat before cutover; formal treatment plan required
Medium (5-9) | Treat or accept with owner signoff; track in register
Low (1-4) | Accept and monitor; review annually
Risk Summary (live counts)
Total risks identified:
Inherent Critical:
Inherent High:
Residual Critical:
Residual High:
Residual Medium-High or below:

## Register
Tejaswini Dondeti — Portfolio Sample • tejaswinidondeti.github.io • Read-only preview — please do not edit or redistribute
Risk Register — TechStart Cloud Migration
Risk ID | Risk Title | Risk Description | Asset Affected | Inherent Likelihood (1-5) | Inherent Impact (1-5) | Inherent Score | Inherent Level | Treatment Strategy | Control(s) — ISO 27001 Annex A | NIST CSF Function | Risk Owner | Residual Likelihood (1-5) | Residual Impact (1-5) | Residual Score | Residual Level
R-01 | Unauthorized access to customer database during migration | Misconfigured IAM policies, weak credentials, or exposed endpoints during DMS migration expose 5M+ customer PII records to unauthorized access (external attacker or internal actor). Exploitation leads to data exfiltration and regulatory breach. | Customer PII Database (RDS) | 4 | 5 |  |  | Treat (Mitigate) | A.5.15 Access control; A.5.17 Authentication information; A.8.2 Privileged access rights; A.8.5 Secure authentication; A.8.24 Cryptography | Protect (PR.AC, PR.DS) | CISO / Cloud Platform Lead | 2 | 4
R-02 | IAM misconfiguration granting excessive privileges | Overly permissive IAM roles, wildcard actions, or forgotten break-glass accounts create paths to privilege escalation across the AWS Organization. A single misconfiguration could allow lateral movement to production RDS. | AWS IAM Identity Layer | 4 | 5 |  |  | Treat (Mitigate) | A.5.15 Access control; A.5.16 Identity management; A.8.2 Privileged access rights; A.8.3 Information access restriction | Protect (PR.AC); Detect (DE.CM) | Cloud Platform Lead | 1 | 5
R-03 | Data corruption during migration pipeline | DMS replication lag, schema mismatch, or network interruption causes data integrity loss (dropped rows, truncated fields) during the cutover window. Affects referential integrity and downstream reporting. | DMS Migration Pipeline; Customer PII DB | 3 | 5 |  |  | Treat (Mitigate) | A.8.13 Information backup; A.8.14 Redundancy; A.5.30 ICT readiness for BC; A.8.24 Cryptography (integrity) | Protect (PR.DS); Recover (RC.RP) | DBA / Cloud Platform Lead | 2 | 3
R-04 | Data residency violation under GDPR / customer DPAs | Default AWS multi-region replication or misconfigured backup destinations send EU customer PII outside approved regions, violating GDPR Article 44-49 and contractual DPA terms. Leads to regulatory fines and customer contract breach. | Customer PII Database; Backup Snapshots | 3 | 4 |  |  | Treat (Mitigate) | A.5.31 Legal/regulatory requirements; A.5.34 Privacy and protection of PII; A.5.23 Information security for cloud services; A.8.10 Information deletion | Identify (ID.GV); Protect (PR.DS) | DPO / Legal | 2 | 2
R-05 | Service disruption during cutover window | Cutover fails or exceeds planned 4-hour window; customers experience outage exceeding SLA. Causes revenue loss, SLA credit obligations, and reputational damage. Rollback path exists but adds 6 more hours of downtime. | Customer-facing SaaS Platform | 3 | 4 |  |  | Treat (Mitigate) | A.5.30 ICT readiness for BC; A.8.14 Redundancy; A.8.13 Information backup; A.5.24 Incident management | Respond (RS.RP); Recover (RC.RP) | VP Engineering | 2 | 2
R-06 | Insufficient logging and monitoring coverage post-migration | Gaps in CloudTrail, VPC Flow Log, or application log collection during transition mean security events in the new environment go undetected. First 90 days post-cutover are highest risk. | AWS Production Environment | 3 | 4 |  |  | Treat (Mitigate) | A.8.15 Logging; A.8.16 Monitoring activities; A.5.25 Assessment of security events | Detect (DE.CM, DE.AE) | SRE / Cloud Platform Lead | 2 | 3
R-07 | Vendor concentration and supply-chain dependency on AWS | Over-reliance on AWS creates single-provider risk; regional outage or policy change could disrupt service. Exit cost and portability are limited. | AWS Provider | 2 | 4 |  |  | Accept (with monitoring) | A.5.19 Supplier relationships; A.5.21 ICT supply chain; A.5.22 Monitoring of supplier services | Identify (ID.SC) | CISO / Legal | 2 | 4

## Heat Map - Inherent
Tejaswini Dondeti — Portfolio Sample • tejaswinidondeti.github.io • Read-only preview — please do not edit or redistribute
5x5 Risk Heat Map — Inherent Risk
Likelihood →
|  | 1 - Rare | 2 - Unlikely | 3 - Possible | 4 - Likely | 5 - Almost Certain
| 5 - Catastrophic | 5 | 10 | R-03 (score 15) | R-01 R-02 (score 20) | 25
| 4 - Major | 4 | R-07 (score 8) | R-04 R-05 R-06 (score 12) | 16 | 20
| 3 - Moderate | 3 | 6 | 9 | 12 | 15
↑ Impact | 2 - Minor | 2 | 4 | 6 | 8 | 10
| 1 - Negligible | 1 | 2 | 3 | 4 | 5
Legend
Critical (20-25)
High (15-19)
Medium-High (10-14)
Medium (5-9)
Low (1-4)

## Heat Map - Residual
Tejaswini Dondeti — Portfolio Sample • tejaswinidondeti.github.io • Read-only preview — please do not edit or redistribute
5x5 Risk Heat Map — Residual Risk (post-treatment)
Likelihood →
|  | 1 - Rare | 2 - Unlikely | 3 - Possible | 4 - Likely | 5 - Almost Certain
| 5 - Catastrophic | R-02 (score 5) | 10 | 15 | 20 | 25
| 4 - Major | 4 | R-01 R-07 (score 8) | 12 | 16 | 20
| 3 - Moderate | 3 | R-03 R-06 (score 6) | 9 | 12 | 15
↑ Impact | 2 - Minor | 2 | R-04 R-05 (score 4) | 6 | 8 | 10
| 1 - Negligible | 1 | 2 | 3 | 4 | 5
Legend
Critical (20-25)
High (15-19)
Medium-High (10-14)
Medium (5-9)
Low (1-4)

## Scoring Criteria
Tejaswini Dondeti — Portfolio Sample • tejaswinidondeti.github.io • Read-only preview — please do not edit or redistribute
Likelihood and Impact Scoring Criteria
Likelihood
Rating | Label | Annual Probability | Description
1 | Rare | < 5% | Event unlikely to occur during migration phase; no known precedent.
2 | Unlikely | 5–25% | Event could occur but requires coincidence of factors or motivated attacker.
3 | Possible | 25–50% | Event has occurred in comparable organizations; should be planned for.
4 | Likely | 50–75% | Event has occurred previously at TechStart or is common in cloud migrations.
5 | Almost Certain | > 75% | Event is expected to occur without active control intervention.
Impact
Rating | Label | Financial | Operational / Reputational / Regulatory
1 | Negligible | < $10K | Minimal disruption; internal only; no regulatory or customer impact.
2 | Minor | $10K–$100K | Short disruption (< 1h); minor customer inconvenience; internal remediation.
3 | Moderate | $100K–$1M | Service degradation 1–4h; customer complaints; possible SLA credits.
4 | Major | $1M–$10M | Outage > 4h; significant customer contract exposure; regulator notification; media coverage.
5 | Catastrophic | > $10M | Mass data breach; regulatory fines (GDPR up to 4% global revenue); loss of customer trust; existential threat.