## Cover
Tejaswini Dondeti — Portfolio Sample • tejaswinidondeti.github.io • Read-only preview — please do not edit or redistribute
TechStart Inc.
Risk Remediation Tracker
Cloud Migration — ISO/IEC 27001:2022 Risk Treatment
Document ID: | TS-ISMS-RT-001
Version: | 1.0
Last Updated: | Q3 2024 (weekly review)
Owner: | GRC Lead / PMO
Linked Documents: | TS-ISMS-RR-001 Risk Register; TS-ISMS-SOA-001 Statement of Applicability
Review Cadence: | Weekly during migration; biweekly post-cutover; monthly steady-state
Escalation: | Any Blocked or P1 overdue item escalates to CISO; Board notification if unresolved > 30 days
Status Legend
Not Started
In Progress
Blocked
Completed
Verified
Summary (live counts)
Total remediation items:
Not Started:
In Progress:
Blocked:
Completed:
Verified:
Percent Complete:

## Tracker
Tejaswini Dondeti — Portfolio Sample • tejaswinidondeti.github.io • Read-only preview — please do not edit or redistribute
Risk Remediation Tracker
Task ID | Linked Risk | Task Title | Description / Deliverable | Linked Control(s) — Annex A | Priority | Owner | Target Date | Completion Date | Status | % Complete | Evidence Link | Notes
T-001 | R-01 | Enforce MFA on all AWS console users | Okta-enforced MFA via SAML federation; no exceptions. Configure IAM deny-all-without-MFA policy. | A.5.17; A.8.5 | P1 - Critical | Cloud Platform Lead | 2024-08-15 | 2024-08-12 | Verified | 100% | Okta admin export + IAM policy in Terraform PR #412 | Verified via access-review screenshot.
T-002 | R-01 | Deploy RDS encryption and KMS key policies | KMS CMK with least-privilege policy; RDS encryption at rest enabled; PI key rotation annual. | A.8.24; A.5.33 | P1 - Critical | DBA | 2024-08-20 | 2024-08-18 | Verified | 100% | KMS key ARN + RDS modify-db log | Cross-account usage denied by SCP.
T-003 | R-01 | Implement CloudTrail organization trail with S3 Object Lock | Org-wide CloudTrail to dedicated logging account; S3 bucket with Object Lock (WORM) 365-day retention. | A.5.28; A.8.15 | P1 - Critical | SRE | 2024-08-25 | 2024-08-24 | Completed | 100% | CloudTrail ARN; S3 bucket policy | Verification pending GRC review.
T-004 | R-01 | Database activity monitoring (DAM) rollout | Enable RDS enhanced monitoring + Performance Insights; forward anomalous queries to SIEM. | A.8.16; A.5.25 | P2 - High | DBA / SRE | 2024-09-30 |  | In Progress | 60% |  | SIEM onboarding backlog item SEC-221.
T-005 | R-02 | Enable IAM Access Analyzer org-wide | Deploy Access Analyzer in all member accounts; findings routed to Security Slack channel. | A.5.15; A.8.2 | P1 - Critical | Cloud Platform Lead | 2024-08-10 | 2024-08-09 | Verified | 100% | Access Analyzer console export; Terraform module
T-006 | R-02 | Implement Service Control Policies (SCPs) | Deny dangerous actions (root user access, disabling CloudTrail, modifying IAM without MFA) at Organization level. | A.5.15; A.8.22 | P1 - Critical | Cloud Platform Lead | 2024-08-15 | 2024-08-14 | Verified | 100% | SCP JSON in IaC repo | Reviewed by external auditor in pre-assessment.
T-007 | R-02 | Remove wildcard IAM policies from legacy roles | Audit all IAM policies, replace Action: "*" with scoped permissions; document exceptions. | A.8.2; A.8.3 | P1 - Critical | Cloud Platform Lead | 2024-08-30 | 2024-08-28 | Completed | 100% | Policy diff report | 5 exceptions documented with owner signoff.
T-008 | R-02 | Quarterly IAM access review process | Document process; first review scheduled post-cutover. Automated report via Access Analyzer + Okta report. | A.5.18 | P2 - High | GRC Lead | 2024-10-15 |  | In Progress | 40% |  | SOP drafted; first cycle pending.
T-009 | R-03 | DMS replication validation with checksums | Enable DMS validation task; compare row counts and CRC checksums pre/post migration. | A.8.24; A.5.14 | P1 - Critical | DBA | 2024-09-05 | 2024-09-04 | Verified | 100% | DMS validation report | Zero discrepancies across 5M rows.
T-010 | R-03 | Multi-AZ RDS with automated backups (35-day) | Deploy RDS in Multi-AZ with automated backup retention 35 days; cross-region snapshot copy to us-west-2. | A.8.13; A.8.14; A.5.30 | P1 - Critical | DBA | 2024-08-18 | 2024-08-16 | Verified | 100% | RDS config; snapshot-copy rule
T-011 | R-03 | Quarterly restore test | Restore to isolated account, validate schema + row counts, document RTO achieved. | A.8.13; A.5.30 | P2 - High | DBA | 2024-10-30 |  | Not Started | 0% |  | First test scheduled for Oct.
T-012 | R-04 | Region-lock SCP for EU customer data | SCP denies resource creation outside approved regions (us-east-1, us-west-2 for US; eu-central-1 for EU). | A.5.31; A.5.23 | P1 - Critical | Cloud Platform Lead / DPO | 2024-08-22 | 2024-08-20 | Verified | 100% | SCP JSON; DPIA update
T-013 | R-04 | Complete DPIA for cloud migration | GDPR Article 35 DPIA; reviewed by DPO and Legal; filed with ROPA. | A.5.34 | P1 - Critical | DPO | 2024-08-10 | 2024-08-08 | Verified | 100% | DPIA v1.2 signed; ROPA entry #D-2024-014
T-014 | R-04 | Update customer DPAs with new sub-processor list | Notify customers of AWS as processor under GDPR Art. 28; update DPA where required. | A.5.20; A.5.31 | P2 - High | Legal | 2024-09-30 |  | In Progress | 70% |  | 45/200 customers notified; 155 remaining.
T-015 | R-05 | Cutover runbook with rollback steps | Written runbook, rehearsed twice; explicit rollback trigger criteria and timings documented. | A.5.29; A.5.30 | P1 - Critical | VP Engineering | 2024-09-15 | 2024-09-12 | Verified | 100% | Runbook v2.0; dress rehearsal log
T-016 | R-05 | Customer communication plan | Advance notice 30/14/7/1 day; status page; support team scripted. | A.5.24; A.5.26 | P2 - High | Customer Success / Legal | 2024-09-10 | 2024-09-08 | Completed | 100% | Comm plan; draft emails approved | Verification pending comms send.
T-017 | R-05 | Incident response tabletop exercise | Simulate cutover failure, rollback decision, and customer escalation. Document lessons learned. | A.5.26; A.5.27 | P2 - High | CISO / VP Eng | 2024-09-18 | 2024-09-17 | Verified | 100% | Tabletop after-action report | 3 findings opened as follow-ups.
T-018 | R-06 | Deploy centralized log aggregation | All CloudTrail, VPC Flow, and application logs to central S3 + SIEM; 365-day hot + 7-year cold retention. | A.8.15 | P2 - High | SRE | 2024-10-31 |  | In Progress | 50% |  | S3 architecture complete; SIEM onboarding in flight.
T-019 | R-06 | GuardDuty org-wide with auto-remediation | GuardDuty enabled in all regions and accounts; critical findings trigger Lambda remediation + PagerDuty. | A.8.16; A.5.25 | P2 - High | SRE | 2024-09-25 | 2024-09-22 | Completed | 100% | GuardDuty config; Lambda ARN
T-020 | R-06 | 90-day post-migration monitoring review | Structured review of all security events during first 90 days post-cutover; lessons learned report. | A.5.27; A.8.16 | P3 - Medium | GRC Lead | 2024-12-15 |  | Not Started | 0% |  | Scheduled for Dec-2024.
T-021 | R-07 | Document cloud exit strategy | Written exit plan: data egress process, alternative provider shortlist, estimated cost and timeline. | A.5.19; A.5.22 | P3 - Medium | CISO | 2024-11-30 |  | Not Started | 0% |  | Risk accepted; documentation underway.
T-022 | Cross | Publish Information Security Policy | Approve and publish core ISMS policy; distribute to all staff; confirm attestation. | A.5.1 | P2 - High | CISO | 2024-09-01 | 2024-08-30 | Verified | 100% | Policy v1.0 signed by CEO
T-023 | Cross | Publish Access Control Policy | Document and distribute; link to IAM SOPs. | A.5.15; A.5.18 | P2 - High | CISO | 2024-09-05 | 2024-09-03 | Verified | 100% | Policy v1.0
T-024 | Cross | Publish Data Classification Policy | Document classification tiers and handling requirements; train staff. | A.5.12; A.5.13 | P2 - High | DPO | 2024-09-10 | 2024-09-08 | Completed | 100% | Policy v1.0 | Training rollout in progress.
T-025 | Cross | Conduct ISO 27001 internal audit | Internal audit against ISMS; document findings; close out before external pre-assessment. | A.5.35; A.5.36 | P3 - Medium | GRC Lead | 2025-02-28 |  | Not Started | 0% |  | Scheduled Q1 2025.

## By Risk
Tejaswini Dondeti — Portfolio Sample • tejaswinidondeti.github.io • Read-only preview — please do not edit or redistribute
Remediation Coverage by Risk
Risk ID | Total Tasks | Verified/Completed | In Progress | Not Started/Blocked | % Closure
R-01
R-02
R-03
R-04
R-05
R-06
R-07
Cross